## Po&Project Status
Total PO Value | Land Development | Boundary Wall | Start Date
55000000 | 100% | 65% | 2025-07-01

## Pay
Bill No | Bill Date | Billed Amount | Tax Amount | Total Bill Amount with Taxes | Retention Amount | TDS | Outstanding Amount | M1 Charges | Finance Charges | Payment Date | Payment Received | Balance
VIPL/SUP/2526/05 | 2026-01-27 | 768000 | 138240 | 906240 | 38400 | 0 | 867840 | 0 | 0 | 2026-02-18 | 728832 | 39168
VIPL/2526/73 | 2026-02-06 | 768000 | 138240 | 906240 | 38400 | 15360 | 852480 | 0 | 0 | 2026-02-18 | 728832 | 39168
VIPL/2526/72 | 2026-02-06 | 165000 | 29700 | 194700 | 8250 | 3300 | 183150 | 0 | 0 |  | 0 | 165000
VIPL/2526/72 | 2026-02-06 | 165000 | 29700 | 194700 | 8250 | 3300 | 183150 | 0 | 0 |  | 0 | 165000

## Daily Expense
Expense Category | Month | Basic Amount | Amount paid
Fuel Expense | Jul , 2025 | 6400 | 6400
Fuel Expense | Aug , 2025 | 41100 | 41100
Fuel Expense | Sep , 2025 | 14411 | 14411
Fuel Expense | Oct , 2025 | 41849.49 | 41850
Fuel Expense | Nov , 2025 | 12170 | 12170
Fuel Expense | Dec , 2025 | 400 | 400
Fuel Expense | Jan , 2026 | 630 | 630
Fuel Expense | Feb , 2026 | 1540 | 1540
Inspection Charges | Aug , 2025 | 267500 | 31565
Inspection Charges | Sep , 2025 | 30000 | 35400
Inspection Charges | Oct , 2025 | 175000 | 175000
Inspection Charges | Nov , 2025 | 175000 | 189065
Inspection Charges | Jan , 2025 | 0 | 247170
Job work | Sep , 2025 | 69000 | 80730
Job work | Dec , 2025 | 82800 | 96876
Job work | Jan , 2026 | 690000 | 0
Machinery Rent | Aug , 2025 | 61693 | 55550
Machinery Rent | Sep , 2025 | 17000 | 22041
Machinery Rent | Nov , 2025 | 44428.81 | 44428.81
Machinery Rent | Feb , 2026 | 76000 | 76000
Printing & stationary | Oct , 2025 | 1400 | 1400
Printing & stationary | Feb , 2026 | 245 | 245
Repair & Maintenance | Aug , 2025 | 1800 | 1800
Repair & Maintenance | Oct , 2025 | 290 | 290
Room rent | Jul , 2025 | 2400 | 2400
Room rent | Aug , 2025 | 6000 | 6000
Room rent | Sep , 2025 | 6000 | 6000
Room rent | Oct , 2025 | 6000 | 6000
Room rent | Nov , 2025 | 6000 | 6000
Room rent | Dec , 2025 | 6000 | 6000
Room rent | Jan , 2026 | 12000 | 12000
Room rent | Feb , 2026 | 6000 | 6000
Safety Items | Sep , 2025 | 1950 | 1950
site Expense | Jul , 2025 | 1900 | 1900
site Expense | Dec , 2025 | 7600 | 7600
site Expense | Feb , 2026 | 350 | 350
Staff Salary | Jul , 2025 | 28903.23 | 27348.74
Staff Salary | Aug , 2025 | 128000 | 121114
Staff Salary | Sep , 2025 | 148000 | 155281
Staff Salary | Oct , 2025 | 128000 | 115114
Staff Salary | Nov , 2025 | 148000 | 131281
Staff Salary | Dec , 2025 | 120000 | 112566
Staff Salary | Jan , 2026 | 175500 | 161679.52
Staff Salary | Feb , 2026 | 125500 | 113479.52
Staff Welfare Expense | Jul , 2025 | 1150 | 1150
Staff Welfare Expense | Aug , 2025 | 3410 | 3410
Travel Expense | Jun , 2025 | 29158.15 | 29158
Travel Expense | Feb , 2026 | 2777 | 2777
Vehicle Rent | Nov , 2025 | 10000 | 10000
Water & Electricty charges | Aug , 2025 | 4500 | 4500
Water & Electricty charges | Sep , 2025 | 569 | 569
Water & Electricty charges | Oct , 2025 | 380 | 380
Water & Electricty charges | Nov , 2025 | 6000 | 6000
Water & Electricty charges | Jan , 2026 | 1208 | 1208
Water & Electricty charges | Feb , 2026 | 938 | 938
Freight | Feb , 2026 | 2100 | 2100
2936950.68

## Pivot
Expense Category | Month | Sum of Basic Amount | Sum of Amount paid
Fuel Expense | Jul , 2025 | 6400 | 6400
Fuel Expense | Aug , 2025 | 41100 | 41100
Fuel Expense | Sep , 2025 | 14411 | 14411
Fuel Expense | Oct , 2025 | 41849.49 | 41850
Fuel Expense | Nov , 2025 | 12170 | 12170
Fuel Expense | Dec , 2025 | 400 | 400
Fuel Expense | Jan , 2026 | 630 | 630
Fuel Expense | Feb , 2026 | 1540 | 1540
Inspection Charges | Aug , 2025 | 267500 | 31565
Inspection Charges | Sep , 2025 | 30000 | 35400
Inspection Charges | Oct , 2025 | 175000 | 175000
Inspection Charges | Nov , 2025 | 175000 | 189065
Inspection Charges | Jan , 2025 |  | 247170
Job work | Sep , 2025 | 69000 | 80730
Job work | Dec , 2025 | 82800 | 96876
Job work | Jan , 2026 | 690000
Machinery Rent | Aug , 2025 | 61693 | 55550
Machinery Rent | Sep , 2025 | 17000 | 22041
Machinery Rent | Nov , 2025 | 44428.81 | 44428.81
Machinery Rent | Feb , 2026 | 76000 | 76000
Printing & stationary | Oct , 2025 | 1400 | 1400
Printing & stationary | Feb , 2026 | 245 | 245
Repair & Maintenance | Aug , 2025 | 1800 | 1800
Repair & Maintenance | Oct , 2025 | 290 | 290
Room rent | Jul , 2025 | 2400 | 2400
Room rent | Aug , 2025 | 6000 | 6000
Room rent | Sep , 2025 | 6000 | 6000
Room rent | Oct , 2025 | 6000 | 6000
Room rent | Nov , 2025 | 6000 | 6000
Room rent | Dec , 2025 | 6000 | 6000
Room rent | Jan , 2026 | 12000 | 12000
Room rent | Feb , 2026 | 6000 | 6000
Safety Items | Sep , 2025 | 1950 | 1950
site Expense | Jul , 2025 | 1900 | 1900
site Expense | Dec , 2025 | 7600 | 7600
site Expense | Feb , 2026 | 350 | 350
Staff Salary | Jul , 2025 | 28903.23 | 27348.74
Staff Salary | Aug , 2025 | 128000 | 121114
Staff Salary | Sep , 2025 | 148000 | 155281
Staff Salary | Oct , 2025 | 128000 | 115114
Staff Salary | Nov , 2025 | 148000 | 131281
Staff Salary | Dec , 2025 | 120000 | 112566
Staff Salary | Jan , 2026 | 175500 | 161679.52
Staff Salary | Feb , 2026 | 125500 | 113479.52
Staff Welfare Expense | Jul , 2025 | 1150 | 1150
Staff Welfare Expense | Aug , 2025 | 3410 | 3410
Travel Expense | Jun , 2025 | 29158.15 | 29158
Travel Expense | Feb , 2026 | 2777 | 2777
Vehicle Rent | Nov , 2025 | 10000 | 10000
Water & Electricty charges | Aug , 2025 | 4500 | 4500
Water & Electricty charges | Sep , 2025 | 569 | 569
Water & Electricty charges | Oct , 2025 | 380 | 380
Water & Electricty charges | Nov , 2025 | 6000 | 6000
Water & Electricty charges | Jan , 2026 | 1208 | 1208
Water & Electricty charges | Feb , 2026 | 938 | 938
Freight | Feb , 2026 | 2100 | 2100
Grand Total |  | 2936950.68 | 2238315.59

## 21 March
Total | [10 empty] | 2936950.68 | 268074 | 3205024.68 | 49870 | 67299.57 | 2739.6 | 3085115.51 | 2238315.59 | 846799.92
S.No | Invoice Date | Payment Date | Month | Invoice No. | Vendor/Employee | Paid By | Client Name | Site | Description | Expense Category | Basic Amount | Tax Amount | Total | TDS | PF | ESIC | Amount payable | Amount paid | Difference | Remark
1 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Choudhary Petroleum | Rahul Rai | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 | 0 | 2000 | 2000 | 0
2 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Choudhary Petroleum | Rahul Rai | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 1000 | 0 | 1000 | 0 | 0 | 0 | 1000 | 1000 | 0
3 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Mayur Madhukar Patil | Shivam Singh | Onix | Hanegaon | Pujan samgri & sweets | site Expense | 500 | 0 | 500 | 0 | 0 | 0 | 500 | 500 | 0
4 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Machhendrar Reddy | Shivam Singh | Onix | Hanegaon | Hotel Stay Charge | Room rent | 800 | 0 | 800 | 0 | 0 | 0 | 800 | 800 | 0
5 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Machhendrar Reddy | Shivam Singh | Onix | Hanegaon | Hotel Stay Charge | Room rent | 1600 | 0 | 1600 | 0 | 0 | 0 | 1600 | 1600 | 0
6 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Jahirodin Mastansab Kabnure | Shivam Singh | Onix | Hanegaon | Mattress & pillow | Staff Welfare Expense | 700 | 0 | 700 | 0 | 0 | 0 | 700 | 700 | 0
7 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Sulfule | Shivam Singh | Onix | Hanegaon | Paid to pandit for Pooja | site Expense | 1100 | 0 | 1100 | 0 | 0 | 0 | 1100 | 1100 | 0
8 | 2025-07-28 | 2025-07-28 | Jul , 2025 |  | Arjun Sivaji Pawar | Shivam Singh | Onix | Hanegaon | JCB operator payment | site Expense | 200 | 0 | 200 | 0 | 0 | 0 | 200 | 200 | 0
9 | 2025-07-29 | 2025-07-29 | Jul , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 1400 | 0 | 1400 | 0 | 0 | 0 | 1400 | 1400 | 0
10 | 2025-07-29 | 2025-07-29 | Jul , 2025 |  | Arjun Sivaji Pawar | Shivam Singh | Onix | Hanegaon | JCB operator payment | site Expense | 100 | 0 | 100 | 0 | 0 | 0 | 100 | 100 | 0
11 | 2025-06-30 | 2025-08-03 | Jun , 2025 |  | Rahul Rai | VIPL_5779 | Onix | Hanegaon | Refund for Site Visit in June 2025 | Travel Expense | 11921 | 0 | 11921 | 0 | 0 | 0 | 11921 | 11921 | 0
12 | 2025-07-30 | 2025-08-03 | Jul , 2025 |  | Sachin | Shivam Singh | Onix | Hanegaon | Blanket | Staff Welfare Expense | 450 | 0 | 450 | 0 | 0 |  | 450 | 450 | 0
13 | 2025-07-31 | 2025-07-31 | Jul , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 |  | 2000 | 2000 | 0
14 | 2025-08-01 | 2025-08-01 | Aug , 2025 |  | Ravi | Shivam Singh | Onix | Hanegaon | Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 |  | 520 | 520 | 0
15 | 2025-08-01 | 2025-08-01 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 |  | 2000 | 2000 | 0
16 | 2025-08-01 | 2025-08-01 | Aug , 2025 |  | Johirodin Mastansab | Shivam Singh | Onix | Hanegaon | Matress and pillow | Staff Welfare Expense | 810 | 0 | 810 | 0 | 0 |  | 810 | 810 | 0
17 | 2025-08-02 | 2025-08-02 | Aug , 2025 |  | Amar Umakant | Vatsinfra_ICICI | Onix | Hanegaon | Room rent security started from 30 july - 30 -08-ust | Room rent | 6000 | 0 | 6000 | 0 | 0 |  | 6000 | 6000 | 0
18 | 2025-08-02 | 2025-08-02 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 |  | 2000 | 2000 | 0
19 | 2025-08-02 | 2025-08-02 | Aug , 2025 |  | Shivaji Govind Pawar | Shivam Singh | Onix | Hanegaon | JCB rent (Reparing charge) paid to Rajesh | Machinery Rent |  | 0 | 0 | 0 | 0 |  | 0 | 1050 | -1050
20 | 2025-08-02 | 2025-08-02 | Aug , 2025 |  | Shivaji Govind Pawar | Shivam Singh | Onix | Hanegaon | JCB rent (JCB operator) paid to Arjun | Machinery Rent | 0 | 0 | 0 | 0 | 0 |  | 0 | 500 | -500
21 | 2025-08-04 | 2025-08-04 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Petrol | Fuel Expense | 510 | 0 | 510 | 0 | 0 |  | 510 | 510 | 0
22 | 2025-08-04 | 2025-08-04 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel | Fuel Expense | 3000 | 0 | 3000 | 0 | 0 |  | 3000 | 3000 | 0
23 | 2025-08-04 | 2025-08-04 | Aug , 2025 |  | Dattatary | Shivam Singh | Onix | Hanegaon | Water Tanker rent | Water & Electricty charges | 1500 | 0 | 1500 | 0 | 0 |  | 1500 | 1500 | 0
24 | 2025-08-06 | 2025-08-06 | Aug , 2025 |  | Shivaji Govind Pawar | Vatsinfra_ICICI | Onix | Hanegaon | JCB rent advance payment | Machinery Rent | 0 | 0 | 0 | 0 | 0 |  | 0 | 10000 | -10000
25 | 2025-08-07 | 2025-08-07 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 3000 | 0 | 3000 | 0 | 0 |  | 3000 | 3000 | 0
26 | 2025-08-07 | 2025-08-07 | Aug , 2025 |  | Shrikrishna Automobile | Shivam Singh | Onix | Hanegaon | Bike Tube | Repair & Maintenance | 350 | 0 | 350 | 0 | 0 |  | 350 | 350 | 0
27 | 2025-08-08 | 2025-08-08 | Aug , 2025 |  | Shri Balaji Pokalwar | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 2900 | 0 | 2900 | 0 | 0 |  | 2900 | 2900 | 0
28 | 2025-08-08 | 2025-08-08 | Aug , 2025 |  | rajnandani Steel Shop | Shivam Singh | Onix | Hanegaon | Utensils | Staff Welfare Expense | 2600 | 0 | 2600 | 0 | 0 |  | 2600 | 2600 | 0
29 | 2025-07-31 | 2025-08-09 | Jul , 2025 |  | Staff Salary | VIPL_5779 | Onix | Hanegaon | 7 Days Salary of Site Engineer & Project Manager | Staff Salary | 28903.23 | 0 | 28903.23 |  | 1554.81 | 0 | 27348.42 | 27348.74 | -0.32
30 | 2025-08-10 | 2025-08-10 | Aug , 2025 |  | Shri Balaji Pokalwar | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 3000 | 0 | 3000 | 0 | 0 |  | 3000 | 3000 | 0
31 | 2025-08-10 | 2025-08-10 | Aug , 2025 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 |  | 520 | 520 | 0
32 | 2025-08-11 | 2025-08-11 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 3000 | 0 | 3000 | 0 | 0 |  | 3000 | 3000 | 0
33 | 2025-08-12 | 2025-08-12 | Aug , 2025 |  | Shribalaji Pokalwar Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 1500 | 0 | 1500 | 0 | 0 |  | 1500 | 1500 | 0
34 | 2025-08-12 | 2025-08-12 | Aug , 2025 | 50500132 | Vgeotech Experts Private Limited | VIPL_5779 | Onix | Hanegaon | Advance Payment for Soil testing and survey | Inspection Charges | 267500 | 48150 | 315650 | 5350 | 0 |  | 310300 | 0 | 310300
35 | 2025-08-13 | 2025-08-13 | Aug , 2025 |  | Shribalaji Pokalwar Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 3000 | 0 | 3000 | 0 | 0 |  | 3000 | 3000 | 0
36 | 2025-08-13 | 2025-08-13 | Aug , 2025 |  | Shrikrishna Automobile | Shivam Singh | Onix | Hanegaon | Bike meter repairing | Repair & Maintenance | 710 | 0 | 710 | 0 | 0 |  | 710 | 710 | 0
37 | 2025-08-13 | 2025-08-13 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 |  | 520 | 520 | 0
38 | 2025-08-14 | 2025-08-14 | Aug , 2025 |  | Shri Balaji Pokalwar | Manshi Tiwari | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 3000 | 0 | 3000 | 0 | 0 |  | 3000 | 3000 | 0
39 | 2025-08-15 | 2025-08-15 | Aug , 2025 |  | CS Ghule | Shivam Singh | Onix | Hanegaon | water can for Guest House | Fuel Expense | 500 | 0 | 500 | 0 | 0 |  | 500 | 500 | 0
40 | 2025-08-18 | 2025-08-18 | Aug , 2025 |  | Ankush Kumar | Vatsinfra_ICICI | Onix | Hanegaon | Tanker Payment | Water & Electricty charges | 3000 | 0 | 3000 | 0 | 0 |  | 3000 | 3000 | 0
41 | 2025-08-21 | 2025-08-21 | Aug , 2025 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike petrol | Fuel Expense | 210 | 0 | 210 | 0 | 0 |  | 210 | 210 | 0
42 | 2025-08-22 | 2025-08-22 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 | 0 | 2000 | 2000 | 0
43 | 2025-08-23 | 2025-08-23 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 900 | 0 | 900 | 0 | 0 | 0 | 900 | 900 | 0
44 | 2025-08-23 | 2025-08-23 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 1500 | 0 | 1500 | 0 | 0 | 0 | 1500 | 1500 | 0
45 | 2025-08-23 | 2025-08-23 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 | 0 | 2000 | 2000 | 0
46 | 2025-08-23 | 2025-08-23 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 | 0 | 520 | 520 | 0
47 | 2025-08-24 | 2025-08-24 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 | 0 | 2000 | 2000 | 0
48 | 2025-08-29 | 2025-08-29 | Aug , 2025 |  | Vgeotech Experts Private Limited | VIPL_5779 | Onix | Hanegaon | Soil testing payment at Hanegaon Site | Inspection Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31565 | -31565 | 10% advance
49 | 2025-08-26 | 2025-08-26 | Aug , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 3000 | 0 | 3000 | 0 | 0 | 0 | 3000 | 3000 | 0
50 | 2025-08-29 | 2025-08-29 | Aug , 2025 |  | Gundaram | Shivam Singh | Onix | Hanegaon | Bike Servicing charge | Repair & Maintenance | 740 | 0 | 740 | 0 | 0 | 0 | 740 | 740 | 0
51 | 2025-09-02 | 02-09-2025 | Sep , 2025 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 | 0 | 520 | 520 | 0
52 | 2025-09-01 | 2025-09-01 | Sep , 2025 |  | SR Hardware | Shivam Singh | Onix | Hanegaon | Safety jacket-15 and Helmet- 15 pcs | Safety Items | 1950 | 0 | 1950 | 0 | 0 | 0 | 1950 | 1950 | 0
53 | 2025-09-01 | 2025-09-01 | Sep , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 2000 | 0 | 2000 | 0 | 0 | 0 | 2000 | 2000 | 0
54 | 2025-08-26 | 2025-09-03 | Aug , 2025 |  | Shivaji Govind Pawar | Vatsinfra_ICICI | Onix | Hanegaon | JCB rent advance | Machinery Rent | 61693 | 0 | 61693 | 1102 | 0 | 0 | 60591 | 10000 | 50591
55 | 2025-06-30 | 2025-09-03 | Jun , 2025 |  | Rahul Rai | Vatsinfra_ICICI | Onix | Hanegaon | Travel Reimburshemnt for Site Visit | Travel Expense | 17237.15 | 0 | 17237.15 | 0 | 0 | 0 | 17237.15 | 17237 | 0.15
56 | 2025-08-31 | 2025-09-10 | Aug , 2025 |  | Shivaji Govind Pawar | Vatsinfra_ICICI | Onix | Hanegaon | Advance for JCB | Machinery Rent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | -4000
57 | 2025-09-07 | 2025-09-07 | Sep , 2025 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 | 0 | 520 | 520 | 0
58 | 2025-08-12 | 2025-09-12 | Aug , 2025 |  | Shivaji Govind Pawar | Vatsinfra_ICICI | Onix | Hanegaon | JCB payment for -08-ust 2025 | Machinery Rent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | -30000
59 | 2025-09-11 | 2025-09-11 | Sep , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
60 | 2025-09-12 | 2025-09-12 | Sep , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | JCB diesel | Fuel Expense | 4351 | 0 | 4351 | 0 | 0 | 0 | 4351 | 4351 | 0
61 | 2025-09-10 | 2025-09-24 | Sep , 2025 | 43 | Alfa Cement Contraction | VIPL_5779 | Onix | Hanegaon | Installation & Supply of Precast | Job work | 69000 | 12420 | 81420 | 690 | 0 | 0 | 80730 | 80730 | 0 | Advance Salary
62 | 2025-09-30 | 2025-09-19 | Sep , 2025 |  | Shivam Singh | VIPL_5779 | Onix | Hanegaon | Advance salary for -09- 2025 | Staff Salary | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | -18000
63 | 2025-09-06 | 2025-09-17 | Sep , 2025 | 18 | Shreein Surveyour | VIPL_5779 | Onix | Hanegaon | Topography Survey | Inspection Charges | 30000 | 5400 | 35400 | 0 | 0 | 0 | 35400 | 35400 | 0 | Gst Payment
64 | 2025-09-01 | 2025-09-18 | Sep , 2025 |  | Amar Umakant | Manshi Tiwari | Onix | Hanegaon | Room rent for -09- 2025 | Room rent | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000 | 6000 | 0
65 | 2025-09-15 | 2025-09-18 | Sep , 2025 |  | Shivaji Govind Pawar | Sadhu | Onix | Hanegaon | Jcb rent final Payment | Machinery Rent | 17000 | 0 | 17000 | 0 | 0 | 0 | 17000 | 22041 | -5041
66 | 2025-09-15 | 2025-09-15 | Sep , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Jcb Diesel | Fuel Expense | 1500 | 0 | 1500 | 0 | 0 | 0 | 1500 | 1500 | 0
67 | 2025-09-22 | 2025-09-22 | Sep , 2025 |  | Amar Umakant | Shivam Singh | Onix | Hanegaon | Electricity bill for-09-2025 | Water & Electricty charges | 569 | 0 | 569 | 0 | 0 | 0 | 569 | 569 | 0
68 | 2025-09-24 | 2025-09-24 | Sep , 2025 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 | 0 | 520 | 520 | 0
69 | 2025-10-01 | 2025-10-05 | Oct , 2025 |  | Amar Umakant | Vatsinfra_ICICI | Onix | Hanegaon | Guest house rent for -10- 2025 | Room rent | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000 | 6000 | 0
70 | 2025-10-07 | 2025-10-07 | Oct , 2025 |  | UPPE Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 510 | 0 | 510 | 0 | 0 | 0 | 510 | 510 | 0
71 | 2025-10-11 | 2025-10-11 | Oct , 2025 | 180 | Geetanjali | Shivam Singh | Onix | Hanegaon | Falx board printing charge | Printing & stationary | 1400 | 0 | 1400 | 0 | 0 | 0 | 1400 | 1400 | 0
72 | 2025-10-13 | 2025-10-13 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
73 | 2025-10-14 | 2025-10-14 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 510 | 0 | 510 | 0 | 0 | 0 | 510 | 510 | 0
74 | 2025-10-14 | 2025-10-14 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
75 | 2025-10-15 | 2025-10-15 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
76 | 2025-10-17 | 2025-10-17 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
77 | 2025-10-18 | 2025-10-18 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
78 | 2025-10-19 | 2025-10-19 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 510 | 0 | 510 | 0 | 0 | 0 | 510 | 510 | 0
79 | 2025-10-19 | 2025-10-19 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 4500 | 0 | 4500 | 0 | 0 | 0 | 4500 | 4500 | 0
80 | 2025-10-23 | 2025-10-23 | Oct , 2025 |  | Chandrayya | Shivam Singh | Onix | Hanegaon | Bike Service Charge | Repair & Maintenance | 290 | 0 | 290 | 0 | 0 | 0 | 290 | 290 | 0
81 | 2025-10-23 | 2025-10-23 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
82 | 2025-10-26 | 2025-10-26 | Oct , 2025 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 299.49 | 0 | 299.49 | 0 | 0 | 0 | 299.49 | 300 | -0.51
83 | 2025-10-26 | 2025-10-26 | Oct , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
84 | 2025-10-27 | 2025-10-27 | Oct , 2025 |  | Amar Umakant | Shivam Singh | Onix | Hanegaon | Guest House Electricity bill | Water & Electricty charges | 380 | 0 | 380 | 0 | 0 | 0 | 380 | 380 | 0
85 | 2025-11-01 | 2025-11-07 | Nov , 2025 |  | Amar Umakant | Manshi Tiwari | Onix | Hanegaon | Guest house rent for -11- 2025 | Room rent | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000 | 6000 | 0
86 | 2025-11-04 | 2025-11-09 | Nov , 2025 |  | Shivaji Govind Pawar | Vatsinfra_ICICI | Onix | Hanegaon | JCB rent for 12 Days | Machinery Rent | 32903 | 0 | 32903 | 0 | 0 | 0 | 32903 | 32903 | 0 | 12903- Paid on 16-12-2025
87 | 2025-10-31 | 2025-10-31 | Oct , 2025 |  | UPPE Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 | 0 | 520 | 520 | 0
88 | 2025-11-05 | 2025-11-05 | Nov , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
89 | 2025-11-06 | 2025-11-06 | Nov , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Diesel for JCB | Fuel Expense | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 5000 | 0
90 | 2025-11-07 | 2025-11-07 | Nov , 2025 |  | Choudhary Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 510 | 0 | 510 | 0 | 0 | 0 | 510 | 510 | 0
91 | 2025-11-13 | 2025-11-13 | Nov , 2025 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 | 0 | 0 | 520 | 520 | 0
92 | 2025-11-17 | 2025-12-16 | Nov , 2025 |  | Shivaji Govind Pawar | Vatsinfra_ICICI | Onix | Hanegaon | 3 Days JCB rent | Machinery Rent | 8225.81 | 0 | 8225.81 | 0 | 0 | 0 | 8225.81 | 8225.81 | 0
93 | 2025-10-31 | 2025-11-11 | Oct , 2025 |  | Staff Salary | VIPL_5779 | Onix | Hanegaon | Staff Salary for Oct 2025 | Staff Salary | 128000 | 0 | 128000 | 0 | 6886 | 0 | 121114 | 115114 | 6000
94 | 2025-11-17 | 2025-11-17 | Nov , 2025 |  | UPPE Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 | 0 | 520 | 0 |  |  | 520 | 520 | 0
95 | 2025-11-14 | 2025-12-16 | Nov , 2025 |  | Kapil Hulram | Vatsinfra_ICICI | Onix | Hanegaon | Local JCB charges | Machinery Rent | 3300 | 0 | 3300 | 0 | 0 | 0 | 3300 | 3300 | 0
96 | 2025-08-31 | 2025-09-11 | Aug , 2025 |  | Staff Salary | VIPL_5779 | Onix | Hanegaon | Staff Salary for August 2025 | Staff Salary | 128000 | 0 | 128000 | 0 | 6885.6 | 0 | 121114.4 | 121114 | 0.4
97 | 2025-10-03 | 2025-09-16 | Oct , 2025 | USPLTI252671 | Urjavinya Solutions Private Limited | VIPL_5779 | Onix | Hanegaon | Design and engineering consultancy | Inspection Charges | 175000 | 31500 | 206500 | 17500 |  |  | 189000 | 175000 | 14000
98 | 2025-11-23 | 2025-11-23 | Nov , 2025 | 250842225K115589 | UPPE Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 310 |  | 310 |  |  |  | 310 | 310 | 0
99 | 2025-09-30 | 2025-10-10 | Sep , 2025 |  | Staff Salary | VIPL_5779 | Onix | Hanegaon | Staff salary for sept 2025 | Staff Salary | 148000 |  | 148000 |  | 10171 | 548 | 137281 | 137281 | 0
100 | 2025-11-28 | 2025-11-28 | Nov , 2025 | 250842225K219185 | UPPE Petroleum | Shivam Singh | Onix | Hanegaon | Petrol for bike | Fuel Expense | 310 |  | 310 |  |  |  | 310 | 310 | 0
101 | 2025-11-18 | 2025-12-01 | Nov , 2025 | USPLTI252679 | Urjavinya Solutions Private Limited | VIPL_5779 | Onix | Hanegaon | Design and engineering consultancy | Inspection Charges | 175000 | 31500 | 206500 | 17500 |  |  | 189000 | 157500 | 31500
102 | 2025-11-30 | 2025-12-16 | Nov , 2025 |  | Staff Salary | VIPL_2754 | Onix | Hanegaon | Staff salary for Nov 2025 | Staff Salary | 148000 |  | 148000 |  | 10171.2 | 547.6 | 137281.2 | 131281 | 6000.2 | 6000 - advance
103 | 2025-12-16 | 2025-12-16 | Dec , 2025 |  | Amar Umakant | Vatsinfra_ICICI | Onix | Hanegaon | Guest House rent | Room rent | 6000 |  | 6000 |  |  |  | 6000 | 6000 | 0
104 | 2025-11-30 | 2025-12-18 | Nov , 2025 |  | Maharaj Singh | Vatsinfra_ICICI | Onix | Hanegaon | Water Tanker payment from 21-30 Nov 2025 (600*10 days) | Water & Electricty charges | 6000 |  | 6000 |  |  |  | 6000 | 6000 | 0
105 | 2025-11-30 | 2025-12-18 | Nov , 2025 |  | Maharaj Singh | Vatsinfra_ICICI | Onix | Hanegaon | Tractor rent payment from 21-30 Nov 2025 (1000*10) | Vehicle Rent | 10000 |  | 10000 |  |  |  | 10000 | 10000 | 0
106 | 2025-12-24 | 2025-12-15 | Dec , 2025 | 45 | Alfa Cement Contraction | VIPL_2754 | Onix | Hanegaon | Installation & Supply of Precast | Job work | 82800 | 14904 | 97704 | 828 |  |  | 96876 | 96876 | 0 | 108606
107 | 2025-12-28 | 2025-12-28 | Dec , 2025 |  | Sayyad Sahil | Amit Pandey | Onix | Hanegaon | Pickup and Labour charges | site Expense | 7600 |  | 7600 |  |  |  | 7600 | 7600 | 0
108 | 2025-12-29 | 2025-12-29 | Dec , 2025 |  | UPPE Petroleum | Amit Pandey | Onix | Hanegaon | Petrol for bike | Fuel Expense | 400 |  | 400 |  |  |  | 400 | 400 | 0
109 | 2026-01-08 | 2026-01-14 | Jan , 2026 |  | Amar Umakant | Manshi Tiwari | Onix | Hanegaon | Room rent | Room rent | 6000 |  | 6000 |  |  |  | 6000 | 6000 | 0
110 | 2026-01-15 | 2026-01-15 | Jan , 2026 |  | Amar Umakant | Shivam Singh | Onix | Hanegaon | Payment of Guest house Electricity bill for Oct,Nov& Dec | Water & Electricty charges | 1208 |  | 1208 |  |  |  | 1208 | 1208 | 0
111 | 2026-01-15 | 2026-01-15 | Jan , 2026 |  | UPPE Petroleum | Shivam Singh | Onix | Hanegaon | Petrol for bike | Fuel Expense | 110 |  | 110 |  |  |  | 110 | 110 | 0 | Amit pandey paid it
112 | 2026-01-17 | 2026-01-17 | Jan , 2026 |  | MS Chaudhary Petroleum Hanegaon | Shivam Singh | Onix | Hanegaon | Petrol for bike | Fuel Expense | 520 |  | 520 |  |  |  | 520 | 520 | 0
113 | 2026-01-30 | 2026-02-02 | Jan , 2026 |  | Amar Umakant | Satish Chandra Mishra | Onix | Hanegaon | Room rent | Room rent | 6000 |  | 6000 |  |  |  | 6000 | 6000 | 0
114 | 2026-01-15 |  | Jan , 2026 | 46 | Alfa Cement Contraction | VIPL_2754 | Onix | Hanegaon | Installation & Supply of Precast | Job work | 690000 | 124200 | 814200 | 6900 |  |  | 807300 |  | 807300 | 108606
115 | 2026-02-09 | 2026-02-09 | Feb , 2026 |  | DTDC | Manshi Tiwari | Onix | Hanegaon | Courier charges | Printing & stationary | 245 |  | 245 |  |  |  | 245 | 245 | 0 | in file
116 | 2026-02-14 | 2026-02-14 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Diesel for JCB | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 4800 | -4800
117 | 2026-02-14 | 2026-02-14 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Petrol for Bike | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 200 | -200 | Bill Not Received
118 | 2026-02-15 | 2026-02-15 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Diesel for JCB | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 4800 | -4800
119 | 2026-02-15 | 2026-02-15 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Petrol for bike | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 200 | -200
120 | 2026-02-17 | 2026-02-17 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Petrol for bike | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 200 | -200
121 | 2026-02-17 | 2026-02-17 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Diesel for JCB | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 4800 | -4800
122 | 2026-02-21 | 2026-03-13 | Feb , 2026 |  | Kapil Hulram | DP Cons. | Onix | Hanegaon | JCB Rent | Machinery Rent | 76000 |  | 76000 |  |  |  | 76000 | 21000 | 55000
123 | 2025-12-31 | 2026-01-13 | Dec , 2025 |  | Staff salary | VIPL_5779 | Onix | Hanegaon | Sttaf Salary Dec 2025 | Staff Salary | 120000 |  | 120000 |  | 6886 | 548 | 112566 | 112566 | 0
124 | 2026-01-31 | 2026-02-13 | Jan , 2026 |  | Staff salary | VIPL_5779 | Onix | Hanegaon | Sttaf Salary Jan 2026 | Staff Salary | 175500 |  | 175500 |  | 13272.48 | 548 | 161679.52 | 161679.52 | 0
125 | 2026-02-26 | 2026-03-11 | Feb , 2026 |  | Staff Salary | VIPL_5779 | Onix | Hanegaon | Sttaf Salary Feb 2026 | Staff Salary | 125500 |  | 125500 |  | 11472.48 | 548 | 113479.52 | 113479.52 | 0
126 | 2025-11-08 | 2025-11-08 | Nov , 2025 |  | Vgeotech Experts Private Limited | VIPL_5779 | Onix | Hanegaon | Advance Payment Vgeotech | Inspection Charges | 0 |  | 0 |  |  |  | 0 | 31565 | -31565
127 | 2025-01-11 | 2025-01-11 | Jan , 2025 |  | Vgeotech Experts Private Limited | VIPL_5779 | Onix | Hanegaon | Soil testing payment at Hanegaon Site | Inspection Charges |  |  | 0 |  |  |  | 0 | 247170 | -247170
128 | 2026-02-19 | 2025-02-19 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Diesel for JCB | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 4800 | -4800
129 | 2026-02-19 | 2025-02-19 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Petrol for bike | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 200 | -200
130 | 2026-02-20 | 2025-02-20 | Feb , 2026 |  | Kapil Hulram- Shri Balaji Pokalwar | Maharaj Singh | Onix | Hanegaon | Diesel for JCB | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 4800 | -4800
131 | 2026-02-22 | 2026-02-22 | Feb , 2026 |  | Kapil Hulram- Sun Petroleum | Maharaj Singh | Onix | Hanegaon | Petrol for bike | Machinery Rent | 0 |  | 0 |  |  |  | 0 | 200 | -200
132 | 2026-02-22 | 2026-02-26 | Feb , 2026 |  | Kapil Hulram | Rahul Rai | Onix | Hanegaon | JCB Rent | Machinery Rent |  |  | 0 |  |  |  | 0 | 30000 | -30000
133 | 2026-02-28 | 2026-03-03 | Feb , 2026 |  | Amar Umakant | Vatsinfra_ICICI | Onix | Hanegaon | Room rent for Feb | Room rent | 6000 |  | 6000 |  |  |  | 6000 | 6000 | 0
134 | 2026-02-11 | 2026-02-11 | Feb , 2026 |  | Musa | Shivam Singh | Onix | Hanegaon | Bike Tube replace | site Expense | 350 |  | 350 |  |  |  | 350 | 350 | 0
135 | 2026-02-11 | 2026-02-11 | Feb , 2026 |  | Vittahal Arjun Rao | Shivam Singh | Onix | Hanegaon | Udgir to Kolhapur Travel | Travel Expense | 400 |  | 400 |  |  |  | 400 | 400 | 0
136 | 2026-02-11 | 2026-02-11 | Feb , 2026 |  | MSRTC | Shivam Singh | Onix | Hanegaon | Kolhapur to Kundal Travel | Travel Expense | 262 |  | 262 |  |  |  | 262 | 262 | 0
137 | 2026-02-11 | 2026-02-11 | Feb , 2026 |  | MSRTC | Shivam Singh | Onix | Hanegaon | Kundal to Malvan Travel | Travel Expense | 51 |  | 51 |  |  |  | 51 | 51 | 0
138 | 2026-02-11 | 2026-02-11 | Feb , 2026 |  | Hotel Anmol | Shivam Singh | Onix | Hanegaon | Malvan to Mitbhav To Malvan auto rent | Freight | 1200 |  | 1200 |  |  |  | 1200 | 1200 | 0
139 | 2026-02-11 | 2026-02-11 | Feb , 2026 |  | MSRTC | Shivam Singh | Onix | Hanegaon | Malvan to Kundal Travel | Travel Expense | 51 |  | 51 |  |  |  | 51 | 51 | 0
140 | 2026-02-12 | 2026-02-12 | Feb , 2026 |  | MSRTC | Shivam Singh | Onix | Hanegaon | Kundal To Kolhapur Travel | Travel Expense | 370 |  | 370 |  |  |  | 370 | 370 | 0
141 | 2026-02-12 | 2026-02-12 | Feb , 2026 |  | MSRTC | Shivam Singh | Onix | Hanegaon | Kolhapur to Gulbarga Travel | Travel Expense | 343 |  | 343 |  |  |  | 343 | 343 | 0
142 | 2026-02-12 | 2026-02-12 | Feb , 2026 |  | MSRTC | Shivam Singh | Onix | Hanegaon | Gulbarga to Aurad sharing cab | Travel Expense | 300 |  | 300 |  |  |  | 300 | 300 | 0
143 | 2026-02-15 | 2026-02-15 | Feb , 2026 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 |  | 520 |  |  |  | 520 | 520 | 0
144 | 2026-02-03 | 2026-02-20 | Feb , 2026 |  | Gulbrga Electricity | Shivam Singh | Onix | Hanegaon | Electricity Charge Geust House Feb to March month | Water & Electricty charges | 504 |  | 504 |  |  |  | 504 | 504 | 0
145 | 2026-02-26 | 2026-02-26 | Feb , 2026 |  | Sun Petroleum | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 520 |  | 520 |  |  |  | 520 | 520 | 0
146 | 2026-02-03 | 2026-03-16 | Feb , 2026 |  | Gulbrga Electricity | Shivam Singh | Onix | Hanegaon | Electricity Charge Geust House | Water & Electricty charges | 434 |  | 434 |  |  |  | 434 | 434 | 0
147 | 2026-02-24 | 2026-03-25 | Feb , 2026 |  | Maharaj Singh | Maharaj Singh | Onix | Hanegaon | Material Packing And Sifting Charge | Freight | 900 |  | 900 |  |  |  | 900 | 900 | 0
148 | 2026-02-24 | 2026-03-29 | Feb , 2026 |  | Maharaj Singh | Shivam Singh | Onix | Hanegaon | Travel Expense | Travel Expense | 1000 |  | 1000 |  |  |  | 1000 | 1000 | 0
149 | 2026-02-24 | 2026-03-29 | Feb , 2026 |  | Maharaj Singh | Shivam Singh | Onix | Hanegaon | Bike Petrol | Fuel Expense | 500 |  | 500 |  |  |  | 500 | 500 | 0

## Sheet4
Expense Category | Basic Amount
Precast | 69000
Precast | 82800 | Row Labels | Without Taxs Basic Amount
Precast | 690000 | Fuel Expense | 116960.49
Fuel Expense | 41100 | Inspection Charges | 647500
Fuel Expense | 400 | Machinery Rent | 199121.81
Fuel Expense | 630 | Precast | 841800
Fuel Expense | 6400 | Grand Total | 1805382.3
Fuel Expense | 12170
Fuel Expense | 41849.49
Fuel Expense | 14411
Machinery Rent | 61693
Machinery Rent | 76000
Machinery Rent | 44428.81
Machinery Rent | 17000
Inspection Charges | 267500
Inspection Charges | 175000
Inspection Charges | 175000
Inspection Charges | 30000